## Sheet1
FMMI Feb 2025 Cutover Communications - System by System Impacts
System Type | System Name | Impact to End Users (Y/N) | Cutoff Date/Time | Startup Date/Time | End User Impact Description
SAP | BW | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAP CRM | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | Solman Monitoring | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | ezFedGrants | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | FNS Grantor | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | Pega | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
Job Scheduler | Control-M | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | ECC | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAP Portal | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | Data Services | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | BOBJ | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAC | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | GRC | Yes | Thursday (1/30) | Wednesday (2/19) | Users should not plan to access GRC from Thursday (1/30) through Wednesday (2/19).
Interface | IAS | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | Concur | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | SmartPay | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | MLINQs | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | NRCS Protracts | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | HHS Grants Solutions | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | ASAP | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | ABCO | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | All Other Agency-Specific Systems | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
SAP | PI/PO | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | IPAC/INTR | Yes | Tuesday (2/11) @ Midnight CT | Wednesday (2/19) | IPAC and INTR invoices must be posted within FMMI by midnight CT on Tuesday (2/11) to be processed on Wednesday (2/12). This will be the last IPAC and INTR runs prior to cutover.
N/A | Disbursements | Yes | Tuesday (2/11) @ Midnight CT | Wednesday (2/19) | Invoices must be posted within FMMI by midnight CT on Tuesday (2/11) to be disbursed on Thursday (2/13). This will be the last disbursement run prior to cutover.
SAP | EnableNow | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
SAP | saprouter | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | ACRWS | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | RITA | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | CPAIS | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | MINC | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
FSDW | FSDW | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Archiving | OpenText | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Secure FTP/Dropbox | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Web Proxy | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Nessus | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.